## Tasks
ID | Type | Name | Display Name | Effort Units | Effort | Dependency | ImmediateParent | Sprint# | URL | Item added in sprint # | Original Effort | Delta of Effort Revision | Item Closed in Sprint# | Notes
0 | Epic | Project Initiation | ProjectInitiation | days | 10 |  |  | 0 | http://agilemanifesto.org/ | 0 | 10 |  | 0
1 | Epic | Epic 1 | Epic1 | days |  | 0 |  | 1,2,3 | https://www.yodiz.com/blog/what-is-epic-in-agile-methodology-definition-and-template-of-epic/ | 0
1a | Story | Baseline anlaysis | BaselineAnalysis | days | 3 |  | 1 | 1 |  | 0 | 3 |  | 1
1b | Story | Understand component 1 | Undestand_comp_1 | days |  |  | 1 | 1,2 |  | 0 |  |  | 1
1a1 | Task | Analyze current code | Analyze_current_code | days | 2 |  | 1b | 1 |  | 0 | 2 |  | 1
1a2 | Task | Write test cases | Write_test_cases | days | 3 | 1a1 | 1b | 1 |  | 0 | 3 |  | 1
1c | Story | Rewrite component 1 | Rewrite_comp_1 | days |  | 1b | 1 | 1,2 |  | 0 |  |  | 2
1c1 | Task | Design component 1 | Design_comp1 | days | 6 |  | 1c | 1,2 |  | 0 | 4 | 2:#1 | 2
1c2 | Task | Implement component 1 | Implement_comp1 | days | 5 | 1c1 | 1c | 2 |  | 0 | 5 |  | 2
1c3 | Task | Handle corner case | Handle_corner_case | days | 4 | 1c1 | 1c | 2 |  | 1 | 4 |  | 2
1d | Story | User testing component 1 | User_testing_comp1 | days | 5 | 1c1 | 1 | 2,3 |  | 0 | 5
2 | Epic | Epic 2 | Epic2 | days |  | 0 |  | 3 |  | 0
2a | Story | Lots of work | Lots_of_work | days | 15 |  | 2 | 3 |  | 0 | 15
2b | Story | Legacy integration | Legacy_integration | days |  |  | 2 | 3 |  | 0
2b1 | Task | Understand legacy system | Understand_legacy_system | days | 8 |  | 2b | 3 |  | 0 | 8
2b2 | Task | Integrate | Integrate | days | 5 | 2b1 | 2b | 3 |  | 0 | 5

## Sprints
# | Start | End | Actuals | Projections
0 | 2018-02-05 | 2018-02-16 | 15 | 10
1 | 2018-02-19 | 2018-03-02 | 12 | 10
2 | 2018-03-05 | 2018-03-16 | 13 | 10
3 | 2018-03-19 | 2018-03-30 |  | 10